## Slide 1
Code-ox Technologies
COX-MSA-VTL-2026-001
PROJECT KICKOFF · JUNE 2026
AIWA × AIKA
Production Deployment
AI-powered patient engagement for Vitality Home Health Services — WhatsApp AI Agent, Voice AI Receptionist & Unified Dashboard.
Prepared by
shabeeb.k@code-ox.com · +966 53 571 6437 · code-ox.com
PROJECT AT A GLANCE
CLIENT
Vitality Home Health Services
Riyadh, Kingdom of Saudi Arabia · ڤيتالتي للخدمات الطبية والتجميلية المنزلية
ENGAGEMENT TYPE
SaaS Platform Deployment
TARGET GO-LIVE
8 Weeks from Today
CONTRACT TYPE
Annual Plan · MSA
3
Core Modules
8 wks
to Go-Live
24/7
AI Coverage
2
Languages
Reference: COX-MSA-VTL-2026-001 · Annual Platform Fee SAR 63,000/year · Governed by Master Services Agreement
Vitality Home Health Services · Confidential · 2026

## Slide 2
Code-ox Technologies
TODAY'S AGENDA
KICKOFF SESSION · JUNE 2026
What We'll Cover Today
01
Project Vision & Goals
The problem, solution & expected outcomes
02
Platform Overview
AIWA, AIKA & Unified Dashboard deep dive
03
Technical Architecture
Integration map & technology stack
04
8-Week Delivery Plan
Phases, milestones & critical dependencies
06
Team & Governance
Contacts & communication cadence
07
Open Questions & Next Steps
Discussion, action items & owners
05
Requirements from Vitality Team
SIP trunk · Nixpend HMS · WhatsApp · SMS · Payment Gateway · Master Data · Branding
CRITICAL PATH

## Slide 3
Code-ox Technologies
PROJECT VISION
THE WHY
Transforming Home Healthcare in Saudi Arabia
Patients deserve seamless 24/7 access. Coordinators deserve fewer missed calls and manual tasks. Vitality deserves to scale without adding headcount.
The Challenge
Missed calls after hours, manual booking friction, and no Arabic-first digital channel for home care patients in Riyadh.
The Solution
24/7 AI agents on WhatsApp & voice — bilingual Najdi Arabic/English, fully integrated with Nixpend HMS.
The Outcome
More confirmed bookings, zero missed after-hours calls, reduced coordinator workload, happier patients.
24/7
Patient Availability
2
Languages
8
Weeks to Go-Live
3
Core Modules
0
Extra Headcount

## Slide 4
Code-ox Technologies
PLATFORM OVERVIEW
THREE CORE COMPONENTS
What We're Building
AIWA
WhatsApp AI Agent
24/7 bilingual patient engagement on WhatsApp — booking, documents, outbound campaigns & coordinator handoff.
Booking
Arabic / EN
Campaigns
Documents
AIKA
Voice AI Receptionist
24/7 inbound calls in Najdi Arabic & English — conversational booking, reminders & therapist confirmations.
Voice Booking
Reminders
Najdi Arabic
Outreach
DASHBOARD
Unified Command Center
Real-time view of conversations, bookings, campaigns & escalations across every channel.
Real-Time
Pipeline
Analytics
Escalations
All modules integrate with:
Nixpend HMS
STC SIP Trunk
WhatsApp API
SMS Gateway
Payment Gateway
Google Maps

## Slide 5
Code-ox Technologies
AIWA — WHATSAPP AI AGENT
MODULE 01
AIWA — WhatsApp AI Agent
Bilingual Conversations
Seamless Arabic + English in the same chat. Auto language detection per message.
Conversational Booking
Service, date/time, location via Google Maps — writes directly to Nixpend HMS.
Document Handling
Accepts prescriptions, referrals, wound photos (JPEG/PNG/PDF) — routes to coordinators.
Booking Confirmation
Auto-sends confirmation with therapist name, service, date & time to patient.
Outbound Campaigns
Broadcast promotions & re-engagement by segment — service type, district, visit history.
Human Handoff
Escalates to coordinator on urgent language or explicit request — with full conversation context.
Multi-Number Support
Up to 3 WhatsApp Business numbers included across different service lines.
Live Dashboard Write-Back
Every booking milestone updates the Unified Dashboard in real time.
Recommendation: A dedicated WhatsApp Business number for AIWA is strongly advised — separate from human-operated numbers to ensure a consistent AI experience.

## Slide 6
MODULE 02
AIKA
Voice AI Receptionist
24/7 Arabic + English inbound voice automation — from initial patient call through appointment confirmation and therapist coordination.
AVAILABILITY
24/7 Inbound Reception
LANGUAGES
Arabic (Najdi) + English
COVERAGE
Voice Booking · Reminders · Therapist Coordination
VOICE CAPACITY
15,000 Minutes / Year Included
Code-ox Technologies
AIKA — Voice AI Receptionist
PRIMARY CAPABILITIES
24/7 Inbound Receptionist
Answers every patient call in Najdi Arabic & English. No missed after-hours calls — ever.
Voice Booking
Conversational appointment booking by phone. Writes directly into Nixpend HMS.
Therapist Confirmation
Automatic outbound call to therapist after every new booking. Language auto-detected (Arabic / English).
OPERATIONAL CAPABILITIES
Automated Patient Reminders
Outbound reminder call 2 hours before every appointment. Reduces no-shows and improves attendance.
Structured Outcome Capture
Logs every call result: Interested · Not Interested Callback Requested · Booking Requested.
Natural Arabic Voice
Premium ElevenLabs Najdi Arabic TTS. Natural, warm and locally familiar to every patient.
SUPPORTING CAPABILITIES
STC SIP Trunk Integration
Uses Vitality's existing STC infrastructure. 1 dedicated AIKA voice DID included in the platform fee.
Voice Campaign Module
Outbound health check reminders, seasonal promotions and patient re-engagement campaigns with retry logic.
Implementation Note: 1 dedicated AIKA voice DID is recommended for cleaner call routing and a consistent patient experience.

## Slide 7
Code-ox Technologies
UNIFIED DASHBOARD
MODULE 03
Unified Command Center
Real-Time Activity
Active WhatsApp conversations & live calls visible in one view.
Booking Pipeline
Requested → Matched → Confirmed → Reminded → Completed.
Therapist View
Availability, district assignments & booking load per therapist.
Campaign Analytics
WhatsApp & voice campaign performance — conversions & outcomes.
Coordinator Escalation Inbox
All escalated chats & calls with full context — ready for takeover.
Export & Reporting
Operational & clinical data export for management & HMS reconciliation.
Coordinator accounts included · Saudi-region data residency · AES-256 at rest · TLS 1.2+ in transit · Full audit trail on all booking actions

## Slide 8
Code-ox Technologies
TECHNICAL ARCHITECTURE
INTEGRATION MAP
How It All Connects
Patient Channels
WhatsApp Business · Voice via STC SIP Trunk
⬇
AI Agents & Dashboard
AIWA (WhatsApp) · AIKA (Voice) · Unified Dashboard
⬇
Nixpend HMS — System of Record
Booking · Patient records · Therapist data · District mapping
⬇
Third-Party Integrations
SMS Gateway · Payment Gateway · Google Maps · Email SMTP
AI & VOICE STACK
OpenAI / Google Gemini
LLM
ElevenLabs TTS
Najdi Arabic voice
Speech-to-Text
Voice transcription
Vapi
Agent orchestration
Twilio
Voice & SMS routing
INFRASTRUCTURE
AWS KSA / Bahrain
Saudi-region cloud
TLS 1.2+ · AES-256
Encryption
Google Maps API
Location & matching
SMTP Email
Notifications
Audit Trail
All actions logged

## Slide 9
Code-ox Technologies
8-WEEK DELIVERY PLAN
DELIVERY TIMELINE
8 Weeks to Go-Live
01
Kickoff & Setup
Project kickoff · Nixpend API review & sandbox access · WhatsApp BSP provisioning · SIP trunk config with STC · Cloud setup · Requirements freeze
Week 1
02
Core Build
AIWA WhatsApp agent · AIKA Voice agent · Nixpend HMS integration · Unified Dashboard · Arabic (Najdi) language tuning · Internal QA
Weeks 2–5
03
Integration & UAT
SMS & payment gateway · End-to-end flow testing · User acceptance testing (UAT) · Bug fixes · Coordinator onboarding (2 × 1hr remote sessions)
Weeks 6–7
04
Go-Live
Production deployment · Live monitoring & go-live support · Handover documentation · Support handoff to ops team
Week 8
Timeline Risk: The 8-week schedule assumes Day 1 sandbox access to Nixpend HMS, STC SIP trunk ready for integration, and SMS/payment providers selected. Delays will shift the Go-Live date.

## Slide 10
Code-ox Technologies
KEY MILESTONES
PROJECT MILESTONES
Success Checkpoints
Week 1
Requirements Freeze + All Sandbox Access
Master data templates submitted · All third-party access provisioned · SIP trunk config confirmed
Week 3
AIWA Alpha — WhatsApp Booking Flow Live
End-to-end WhatsApp booking in Arabic/English writing to Nixpend sandbox confirmed
Week 4
AIKA Alpha + Nixpend Integration Alpha
Voice booking over SIP trunk · Nixpend read/write confirmed · Reminder calls functional
Week 5
Unified Dashboard Build Complete
Real-time pipeline · Coordinator inbox · Campaign metrics all visible
Week 6
Full Integration Test — All Channels
SMS gateway, payment gateway, email notifications — all connected and tested end-to-end
Week 7
UAT Complete + Coordinator Onboarded
Vitality UAT sign-off · All issues resolved · Training sessions complete · Go-Live approved
Week 8
Go-Live — Production Deployment
Live patient traffic · CodeOx on go-live monitoring standby · Handover documentation delivered

## Slide 11
Code-ox Technologies
REQUIREMENTS FROM VITALITY
WHAT WE NEED FROM YOU
The Go-Live Checklist
Every item below sits on the critical path. The earlier Vitality provides these, the sooner we can deliver.
SIP Trunk — STC Telephony
Server credentials, DID numbers, codec config, firewall rules & STC liaison contact
Critical — Week 1
Nixpend HMS API
Full API docs, sandbox URL, credentials, auth method, all required endpoints
Critical — Day 1
WhatsApp, SMS & Payments
Dedicated WA number decision, SMS provider & payment gateway selection
Required — Week 1
Master Data & Content
Service catalog, therapist roster, district map, scripts, branding assets
Required — Week 1
Team & System Access
IT contact, coordinator users, UAT team, executive sponsor, email relay
Required — Week 1
Feedback Turnaround
24–48 business hour response on all review requests and approvals throughout build
Ongoing — All Phases

## Slide 12
Code-ox Technologies
SIP TRUNK REQUIREMENTS
TELEPHONY — STC INFRASTRUCTURE
SIP Trunk Requirements
AIKA connects to Vitality's existing STC SIP trunk. All items below must be confirmed before end of Week 1.
CONNECTIVITY DETAILS
NUMBERS, CAPACITY & NETWORK
SIP server hostname or IP address + port
SIP domain / realm
Transport protocol (UDP / TCP / TLS — TLS preferred)
SIP trunk username, password & auth credentials
Outbound proxy address (if applicable)
DTMF mode (RFC2833 strongly preferred)
Supported codecs (G.711 µ-law/a-law, G.729)
DID number(s) for AIKA (minimum 1 inbound DID)
Maximum concurrent call capacity required
Call routing (business hours vs. after-hours)
Existing IVR to be retired or migrated?
Firewall IP whitelist — CodeOx cloud IPs
SIP ALG on NAT device (must be DISABLED)
STC technical contact name + direct number
Open Question: Has STC already been engaged? DID provisioning typically takes 1–2 weeks with STC. If not yet initiated, this process must begin TODAY to protect the go-live date.

## Slide 13
Code-ox Technologies
NIXPEND HMS INTEGRATION
SYSTEM OF RECORD — HMS / ERP
Nixpend HMS Integration Requirements
Nixpend HMS is the core system of record. Every booking from AIWA and AIKA writes back here. We assume REST API — please confirm.
API ACCESS & ENVIRONMENT
REQUIRED API ENDPOINTS
Full API documentation (Swagger / OpenAPI preferred)
Sandbox / staging environment URL
Sandbox API credentials (username / password or key)
Authentication method (OAuth 2.0 / API Key / JWT?)
API base URL + versioning format
Rate limits and throttling policy
Nixpend technical contact for API support
Patient lookup / search by phone or ID
Create new patient record
Booking creation (service, date, time, patient, therapist)
Booking update / cancellation endpoint
Therapist availability query (by date + district)
Service catalog / service type list
District / zone mapping data
Booking status read-back
Webhook / callback support? (async status push)
Assumption: Standard REST API. If Nixpend uses SOAP, direct DB, or file-based integration, timeline and cost will need revision. | Is Nixpend HMS currently live and sandbox stable?

## Slide 14
Code-ox Technologies
WHATSAPP · SMS · PAYMENT GATEWAY
THIRD-PARTY PROVIDERS
WhatsApp, SMS & Payment Requirements
WhatsApp Business API
Dedicated phone number (new or port existing?)
Meta Business Account (WABA) — existing or new?
Business display name for Meta approval
Business category & description
Facebook Business Manager access
Meta Business Verification status
Note: BSP provisioning included. Meta per-conversation fees are NOT.
SMS Gateway
Provider? (Unifonic / Taqnyat / Msegat / Infobip)
CITC-registered Arabic Sender ID
API credentials (key + secret)
Arabic SMS Unicode support confirmed
Account active and funded
Note: Integration included. Subscription & per-message fees are NOT.
Payment Gateway
Provider? (HyperPay / PayTabs / Moyasar / Checkout)
Merchant account active & verified
Sandbox / test API keys
Production API keys
Payment methods (mada, Visa, Apple Pay)
Note: Integration included. Transaction fees are NOT.

## Slide 15
Code-ox Technologies
DATA, CONTENT & BRANDING
MASTER DATA & CONTENT
What the AI Needs to Know
MASTER DATA (spreadsheet / CSV)
SCRIPTS, BRANDING & CONTENT
Full service catalog (code, Arabic name, English name, description, price)
Therapist roster (name, specialization, districts, mobile, language)
District / zone map of Riyadh (Arabic + English names)
Working hours per service line (incl. weekends & Ramadan)
2026 KSA public holiday calendar
Coordinator contact list (name, role, mobile, WhatsApp)
Escalation trigger keywords / scenarios
Arabic patient greeting script (WhatsApp + voice)
English patient greeting script
Out-of-hours message template (Arabic + English)
FAQ document (top 20+ patient questions + answers)
Escalation handoff message to patient
Vitality logo (SVG or PNG, high-resolution)
Brand color codes (primary & secondary HEX)
Tone of voice guidelines (formal/informal, no-go topics)
Service description copy (used by AI per service)
Templates Provided by CodeOx: We will share structured data collection templates (Excel + Google Sheets) for service catalog, therapist roster and district mapping. Please return completed within 5 business days.

## Slide 16
Code-ox Technologies
TEAM & GOVERNANCE
CONTACTS & COMMUNICATION
Team Structure & Cadence
CODE-OX TEAM
VITALITY TEAM — CONFIRM NAMES TODAY
Technical Project Lead
shabeeb.k@code-ox.com · +966 53 571 6437
Commercial Project Lead
shabeeb.k@code-ox.com · COX-MSA-VTL-2026-001
Standard Support
Mon–Fri 09:00–18:00 AST · 1-day acknowledgement
Executive Sponsor
Final approvals & escalation · Name: ___________________
Technical Contact
Nixpend API + STC SIP liaison · Name: ___________________
Operations Coordinator
UAT lead & training · Name: ___________________
IT Contact
Firewall, network & email relay · Name: ___________________
Weekly
Status updates from CodeOx (Fridays)
24–48h
Feedback turnaround from Vitality
Quarterly
Review meetings post go-live

## Slide 17
Code-ox Technologies
OPEN QUESTIONS
DISCUSSION
Open Questions for Today
1
STC SIP Trunk — Engagement Status
Has STC been contacted? Provisioning takes 1–2 weeks — we may need to start TODAY.
2
Nixpend HMS — API Readiness
Is the API documented and stable? Are there known limitations? Is sandbox available now?
3
WhatsApp Number Decision
New dedicated number or port an existing one? Existing Meta Business Account?
4
SMS & Payment — Provider Shortlisted?
If not, we recommend Unifonic (SMS) and Moyasar or HyperPay (payments) for Saudi compliance.
5
Campaigns — Week 8 or Phase 2?
Are AIWA outbound marketing and AIKA voice campaigns in scope for the initial go-live?
6
UAT Team — Available Weeks 6–7?
We need named technical and operational UAT participants. Please confirm availability.
7
Internal PDPL / Data Privacy
Internal data policies to align with? Patient consent flow or retention requirements?
8
Post-Go-Live Monitoring
Standard business-hours support sufficient, or Premium 24/7 support needed at launch?
9
Communication Channel Preference
Shared WhatsApp group for day-to-day coordination, or email + weekly video call?
10
Go-Live Date — Confirm & Lock
Business events or peak seasons that would affect the 8-week target?

## Slide 18
Code-ox Technologies
NEXT STEPS
POST-KICKOFF ACTIONS
What Happens This Week
CODE-OX ACTIONS
VITALITY ACTIONS
Provision sandbox cloud environment
Week 1
Tech Lead
Send WhatsApp BSP provisioning checklist
This week
Tech Lead
Share SIP trunk configuration spec
This week
Tech Lead
Share Nixpend API integration questionnaire
This week
Tech Lead
Send data collection templates
This week
Comm Lead
Confirm go-live date + weekly sync schedule
Today
Both teams
Engage STC for SIP trunk / DID provisioning
TODAY ⚡
IT Contact
Share Nixpend API docs + sandbox access
By EOW
Tech Contact
Confirm dedicated WhatsApp number
By EOW
Ops Lead
Confirm SMS & payment gateway selection
By EOW
Ops Lead
Return completed data templates
Week 1
Ops Lead
Name UAT team participants (Weeks 6–7)
Week 1
Exec Sponsor
First Weekly Sync — Date to be confirmed before end of today's session
shabeeb.k@code-ox.com · +966 53 571 6437 · code-ox.com
Confidential · Code-ox Technologies · 2026